## WCAG Roadmap
Issue ID | Affected Component / Feature | Issue Description | WCAG Version | WCAG Success Criterion | Conformance Level (A / AA) | Impact (Low / Medium / High) | Planned Remediation | Temporary Workaround (if any) | Owner | Target Completion Date | Status | Last Reviewed
ERR-1 | Forms | Missing form label | 2.2 | 1.1.1 Non-text Content (Level A) 1.3.1 Info and Relationships (Level A) 2.4.6 Headings and Labels (Level AA) 3.3.2 Labels or Instructions (Level A) | A, AA | Low | Provide an associated label, add a descriptive title attribute to the form control, or reference the label(s) using aria-labelledby. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-2 | Table | Empty table header | 2.2 | 1.3.1 Info and Relationships (Level A) | A | Low | If the table cell is a header, provide text within the cell that describes the column or row. If the cell is not a header or must remain empty (such as the top-left cell in a data table), make the cell a <td> rather than a <th>. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-3 | Teacher Dashboard, Student view | Contrast | 2.2 | 1.4.3 Contrast (Minimum) (Level AA) | AA | Medium | Increase the contrast between the foreground (text) color and the background color. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-4 | Headings | Missing first level heading | 2.2 | 1.3.1 Info and Relationships (Level A) 2.4.6 Headings and Labels (Level AA) | A, AA | Low | If the page presents a main heading, place it within an <h1> element. Add other sub-headings as necessary. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-5 | Links | Redudant links | 2.2 | 2.4.4 Link Purpose (In Context) (Level A) | A | Low | If possible, combine the redundant links into one link and remove any redundant text or alternative text (for example, if a product image and product name are in the same link, the image can usually be given alt=""). | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-6 | Script | Noscript element | 2.2 |  | A | Low | Ensure that scripted content is accessible. The <noscript> content will be presented to very few users, but must be accessible if used. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-7 | Label | Empty form label | 2.2 | 1.1.1 Non-text Content (Level A) 1.3.1 Info and Relationships (Level A) 2.4.6 Headings and Labels (Level AA) 3.3.2 Labels or Instructions (Level A) | A, AA | Low | Ensure that the form label contains text that describes the function of the associated form control. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-8 | Label | Select missing label | 2.2 | 1.3.1 Info and Relationships (Level A) 2.4.6 Headings and Labels (Level AA) 3.3.2 Labels or Instructions (Level A) | A, AA | Low | Ensure that the default option of the select menu presents the purpose of the select menu. If visible label text is present, it is best to associate this text to the select menu. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-9 | Label | Orphaned form label | 2.2 | 1.1.1 Non-text Content (Level A) 1.3.1 Info and Relationships (Level A) 2.4.6 Headings and Labels (Level AA) 3.3.2 Labels or Instructions (Level A) | A, AA | Low | Properly associate the label with its corresponding form control. If there is no corresponding form control, remove the label. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-10 | Alt-text | Incorrect alt-text | 2.2 | 1.1.1 Non-text Content (Level A) | A | Medium | Ensure that the alternative text conveys the content and function of the image accurately and succinctly. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-11 | Alt-text | Null or empty alt-text | 2.2 | 1.1.1 Non-text Content (Level A) | A | Low | Ensure that the image does not convey content or that the content of the image is conveyed in nearby text (e.g., a caption). | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-12 | Links | Empty link | 2.2 | 2.4.4 Link Purpose (In Context) (Level A) | A | Low | Remove the empty link or provide text within the link that describes the functionality and/or target of that link. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-13 | Headings | Possible heading | 2.2 | 1.3.1 Info and Relationships (Level A) 2.4.1 Bypass Blocks (Level A) 2.4.6 Headings and Labels (Level AA) | A, AA | Low | If the paragraph is a section heading, use a heading element instead (<h1>-<h6>). | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-14 | Alt-text | Missing alt-text | 2.2 | 1.1.1 Non-text Content (Level A) | A | Medium | Add an alt attribute to the image. The attribute value should accurately and succinctly present the content and function of the image. If the content of the image is conveyed in the context or surroundings of the image, or if the image does not convey content or have a function, it should be given empty/null alternative text (alt=""). | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-15 | Language | Language missing or invalid | 2.2 | 3.1.1 Language of Page (Level A) | A | Low | Identify the document language using the <html lang> attribute with a valid value (e.g., <html lang="en">). Ensure that all lang attribute values are valid. | No temporary workaround | Development | April 30, 2026 | Fixed | June 16, 2026
ERR-16 | Keyboarding applet | ARIA | 2.2 | 1.1.1 Non-text Content (Level A) 1.3.1 Info and Relationships (Level A) 2.4.6 Headings and Labels (Level AA) 4.1.2 Name, Role, Value (Level A) 2.5.3 Label in Name (Level A) | A | Medium | Ensure the ARIA role, state, or property is used correctly. Use standard HTML accessibility features when possible. | No temporary workaround | Development | 2027 | Open | June 16, 2026
ERR-17 | Keyboarding applet | Contrast | 2.2 | 1.4.3 Contrast (Minimum) (Level AA) | AA | Medium | Increase the contrast between the foreground (text) color and the background color. | No temporary workaround | Development | 2027 | Open | June 16, 2026

## Guidance
Field | Guidance
Issue ID | Unique identifier for tracking (e.g. WCAG-01)
WCAG Version | WCAG 2.1 or WCAG 2.2
WCAG Success Criterion | e.g. 1.4.3 Contrast (Minimum)
Impact | High = blocks access, Medium = significant difficulty, Low = minor issue
Status | Open, Planned, In progress, Blocked, Resolved, Verified
Temporary Workaround | Describe any interim solution available to users
Target Completion Date | Planned remediation completion date
Last Reviewed | Date of last status review